## Gantt Chart
| Tasks | Start Date | End Date | Friday |  |  | Saturday |  |  | Sunday |  |  | Monday |  |  | Tuesday |  |  | Wednesday |  |  | Thursday |  |  | Team Members
1 | Planning | 2021-10-26 | 2021-10-28 | [21 empty] | Krishan Lal
1.1 | Look through the assessment |  |  | Working together in class | [20 empty] | Yogesh
1.2 | Talk about the assessment | [23 empty] | Ramandeep Singh
1.3 | Discuss about the topic
1.4 | Start Research
|  | Total Hours | 84 | 8hr | 8hr | 8hr | 10hr | 10hr | 10hr | 10hr | 10hr | 10hr
2 | Recap | 2021-10-28 | 2021-10-31
2.1 | Give reviews about last week research | [17 empty] | Working together in class
2.2 | Conclusion
2.3 | Decide Topic
2.4 | Plan Layouts | [20 empty] | Working together in class
2.5 | Start Making layouts |  |  | Working together in class | [14 empty] | 4hr | 4hr | 4hr
2.6 | Research about backend coading (Watch youtube vedios) |  |  | 8hr | 8hr | 8hr |  | 10hr |  |  | 10hr |  |  | 10hr | [8 empty] | 8hr | 8hr
[7 empty] | 10hr |  | 10hr | 10hr |  | 10hr | 10hr |  | 10hr
|  | Total Hours | 150
3 | Front end, backend and testing | 2021-11-01 | 2021-11-05 | [13 empty] | 10hr
3.1 | Working on backend and testing |  |  | Working together in class | [14 empty] | Working together in class |  |  | Working together in class
3.2 | Working on layouts | [11 empty] | 10hr | 10hr |  | 10hr
|  |  |  | 8hr | 8hr | 8hr | [8 empty] | 10hr |  | 10hr |  | 4hr | 4hr | 4hr | 8hr | 8hr | 8hr
|  | Total hours | 120
|  | 2021-11-06 | 2021-11-09
4 | Database, Layouts and Activities And Testing
4.1 | working on database and testing |  |  | Working together in class
4.2 | working on layouts
4.3 | working on activities |  |  | 8hr | 8hr | 8hr
4.4 | working on layouts | [5 empty] | 10hr | 10hr |  | 10hr | 10hr |  | 10hr | 10hr |  | 10hr | 10hr
4.5 | Working on documentation | [13 empty] | 10hr |  |  | 10hr | Working together in class |  |  | Working together in class
|  | Total hours | 160
[19 empty] | 4hr | 4hr | 4hr | 8hr | 8hr | 8hr

## UI Prototype
Wireframes

## Daily Meetings
First Week
Start Date | 2021-10-26
End date | 2021-10-27 | Team Members | Questions | Monday | Tuesday | Wednesday
|  | krishan Lal | What did you do yesterday?
|  |  | What will you work on today? |  |  | Read Assessment
|  |  | Do You have any obstacles? |  |  | No Obstacles
|  | Yogesh | What did you do yesterday?
|  |  | What will you work on today? |  |  | Read Assessment
|  |  | Do You have any obstacles? |  |  | No Obstacles
|  | Ramanpreet Singh | What did you do yesterday?
|  |  | What will you work on today? |  |  | Read Assessment
|  |  | Do You have any obstacles? |  |  | Face littlebit difficulty to understand the assessment but i will be able to understand after discussing with my team members
Second Week
Start Date | 2021-11-01
End Date | 2021-11-03 | Team Members | Question | Monday | Tuesday | Wednesday
|  | krishan Lal | What did you do yesterday? | Worked on Database | Worked on Database | Worked on Database
|  |  | What will you work on today? | Still work on Database | Working on Database | Working on Database
|  |  | Do You have any obstacles? | face some obstacles in some steps | face obstacles discuss with group members | face issues while doing coading discuss with group members
|  | Yogesh | What did you do yesterday? | Worked on Models and helped group members in their issues | Worked on Models and help group members | Worked on Models
|  |  | What will you work on today? | Working on Models | Working on Models and also helping sahibjot in layout part | Start Working on Activities
|  |  | Do You have any obstacles? | Face problems while doing coading on models | No issues faced | face some obstacles while doing activities
|  | Ramanpreet Singh | What did you do yesterday? | Worked on layouts | Worked on layouts | Worked on layouts
|  |  | What will you work on today? | Working on layouts | Working on layouts and going to discuss about some steps with my group members | Working on layouts and start thinking about presentation
|  |  | Do You have any obstacles? | I faced many issues while desiging layout but I solved by discussing with my team members | No obstacles | No Issues
Third Week
Start date | 2021-11-08
End date | 2021-11-10 | Team Members | Question | Monday | Tuesday | Wednesday
|  | krishan Lal | What did you do yesterday? | Worked on database | Worked on activities | Worked on activities and documentation
|  |  | What will you work on today? | Start working on activities | Still working on activities and start documentation | Working on activities and documentation
|  |  | Do you have any obstacles? | I faced some obstacles while making activities | face some issues discus with group members | No issues
|  | Yogesh | What did you do yesterday? | Worked on activities | worked on activities and documentation | Yesterday i worked on documentation
|  |  | What will you work on today? | Working on activities and documentation | I will work on documentation today | I will work on documentation
|  |  | Do you have any obstacles? | i faced some issues in activities | no issues | no issues
|  | Ramanpreet Singh | What did you do yesterday? | Yesterday i worked on layouts | Yesterday i start the question answer part | Yesterday i compeleted the question answer part
|  |  | What will you work on today? | I will start the Question answer part | Today i will try to compelete the question answer part | today i will start the other documentation
|  |  | Do you have any obstacles? | I faced issues in finding the answers of questions | No issues | No issues

## Testing2
Usability Testing
Usability and Acessability | Agree | Neutral | Disagree | Unsure | Comments
The app is load in android | Yes
Saplash activity page opens while run | Yes
The page is self explanatory and i know how to use it | Yes
Functionality
All the buttons work correctly | Yes
Crud Opreation | Yes
Can Add,Update,Remove and View as well | Partial |  | Update button is not working
Readibility
The font are suitable and easy to read | Yes
The Size and style of the font is easy to read | Yes
The combination between text color and background looks easy to read | Yes
There is sufficient spacing to make the pages easy to read | Yes